## Testing Check
Tester Name | Tester Email | Test Case # | Test Description | Pass/Fail | Bug # | Date/Time | Notes
Ashlei Jones | ashlei.jones@detroitlabs.com | 1 | User logs in successfully | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 1.01 | User does not have a valid username | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 1.02 | User does not have a valid password | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 1.03 | User cannot login with blank username and password | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 2 | User can populate current date by pressing a "Today" button | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 2.01 | User can populate the date manually | Fail |  |  | The calendar does not appear on the first click. It does appear on any proceeding clicks, though.
Ashlei Jones | ashlei.jones@detroitlabs.com | 2.02 | User can populate time manually | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 2.03 | User cannot enter time in a nonstandard format | Deleted-No longer needed
Ashlei Jones | ashlei.jones@detroitlabs.com | 2.04 | User cannot pick two times at once | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 2.05 | User should be able to hit "Next" button to move to next step | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 2.06 | User should be able to hit "Clear" button to clear out the date and time and start over again | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 3 | View Emotions to pick from | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 3.01 | User can choose one emotion | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 3.02 | User can choose all emotions | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 3.03 | User can hit "Done" and move to next step | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 3.04 | User can hit "Clear" and to remove choices | Fail |  |  | The clear button makes the selected buttons lose their styling.
Ashlei Jones | ashlei.jones@detroitlabs.com | 3.05 | User can add an emotion | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 3.06 | User can deselect an emotion | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4 | User should see a screen to enter the factors leading to emotion | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.01 | User should be able to enter location | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.02 | User should be not able to enter location longer than 25 characters | Fail |  |  | I don't get an error when I enter a text field of more than 25 characters.
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.03 | User should be able to choose an environment | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.04 | User should be able to manually enter an enviroment if choose "other" | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.05 | User should be able to enter names of other people around them at the time of the emotion | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.06 | User should be able to list any external factors that contibuted to their emotion | Fail |  |  | The field updated to 'baby crying'. I believe that this is what was meant to happen (edit the test case?)
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.07 | User should be able to list any thoughts that contibuted to their emotion | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.08 | User should be able to make any other notes they wish to make | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.09 | User should be able to save the entry | Fail |  |  | The button says 'submit' not 'done'. (edit the test case). Otherwise, this is a pass.
Ashlei Jones | ashlei.jones@detroitlabs.com | 4.1 | User should be able to clear the entry | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 5 | User should be able to view data table | Pass
Ashlei Jones | ashlei.jones@detroitlabs.com | 5.01 | User should be able to return to date/entry page | Pass
|  | Pass Rate | 83.87%
Most failed test cases in the Trigger/Situation Entry cases